## Document
Sr.No | Document Name | STL submitted document name (Latest version) | Status | Initial Release Date | Last Release Date | Pending Action | Owner | Verified by | Path | Comment
1 | Mediation & Reporting SRS | 2019_03_07_STL_SRS_DMC_Report_Mediation Vs 8.0 | Completed | 2018-12-20 | 2019-03-07 | NA | Deepak Browne | DMC | \\172.24.11.10\Sterlite\1_SRS
2 | Report Annexure | Multiple files | Completed | 2019-02-18 | 2019-02-18 | NA | Deepak Browne | DMC | \\172.24.11.10\Sterlite\1_SRS\Annexure
3 | CEIR SRS | DMC_Sterlite_CEIR_SRS_11Mar2019_v02 | Completed | 2019-01-20 | 2019-03-14 | NA | Sarju | DMC
4 | Infrastructure Delivery | 2019_05_02_Infrastructure Delivery For DMC_Mediation_Reporting &EIR | Completed | 2019-04-04 | 2019-05-02 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\2_HW_Checklist
5 | Infra Installation Plan | Infra_Installation_Plan_v0.2 | Completed | 2018-12-24 | 2018-12-25 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\1_Infra_Installation_Plan
6 | Physical Connectivity Diagram | DMC - Physical Connectivity Diagram_v1.0 | Completed | 2019-02-13 | 2019-03-01 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\2_Connectivity_Diagram
7 | Rack Diagram | Sterlite_Rack Diagram V5 | Completed | 2018-12-18 | 2019-04-18 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\3_Rack_Diagram
8 | Infra Size & Weight | Details of Infra Size_Weight_0.2 | Completed | 2018-12-18 | 2018-12-19 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\3_Rack_Diagram
9 | IP Planning | DMC IP Planning - v.6.0 | Completed | 2019-01-31 | 2019-07-09 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\4_IP_Planning
10 | IP VLAN Details | IP_VLAN_Details_v.1.0 | Completed | 2019-02-05 | 2019-02-05 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\4_IP_Planning
11 | Deployment Preparation Worksheet | Deployment Preparation Worksheet_v2.9 | Completed | 2019-04-23 | 2020-01-29 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\Deployment Preparation Worksheet
12 | Infrastructure Application Installation | STL_DMC_Infrastructure_App_Installation_V.2.0 | Completed | 2019-04-15 | 2019-04-22 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\5_Server_Deployment_Preparation
13 | Server Hardening | Multiple files | Completed | 2019-01-31 | 2020-01-06 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\Server Hardening
14 | Backup Solution | DMC - Backup Solution_v1.0 DMC_CommVault_Backup_Software_Training_v1.0 | Completed | 2019-03-01 | 2019-08-09 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\7_Backup Solution
15 | Hardware Detail | Backup Hardware Details_DMC Storage | Completed | 2018-12-24 | 2018-12-24 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\8_Hardware Details
16 | OS_Software_Package_Module_Details | OS_Software_Package_Module_Details | Completed | 2019-06-06 | 2019-06-06 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\9_OS_Software_Package_Module_Details
17 | Switch Configuration | DMC Switch Configuration | Completed | 2019-07-09 | 2019-07-09 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\11_Switch_Configuration
18 | Dynamic Tiering Implementation Plan | Re-configuration Storage_TAR_20191203 Restore status Step1_Data Backup Step2_DB Backup | Completed | 2019-12-09 | 2019-12-25 | NA | Ajay Patel | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\12_Dynamic Tiering Implementation Planning
19 | Server Credential | DMC - Credentials | Completed | 2019-07-08 | 2019-07-08 | NA | Ajay Patel | DMC | Not shared on shared path as its having server credentials, Kindly refer mail with attchment sent on 08-Jul-19. Mail Sub: [Confidential] Details of discussed points today
20 | Sterlite Team Contact Details | Project Team Structure | Completed | 2018-12-07 | 2019-07-09 | NA | Ashish Kapadiya | DMC | \\172.24.11.10\Sterlite\Contact Details
21 | MoM Tracker | Copy of Action_Points_10-Feb to 14-Feb (007) | On-Going | 2018-12-11 | 2020-02-14 | NA | Ashish Kapadiya | DMC | \\172.24.11.10\Sterlite\Governance\MoM Tracker
22 | Monthly Governance | 2020_01_14_RVM_Monthly_Governance_v1.0 | On-Going | 2019-01-17 | 2020-01-14 | NA | Shyam Garg | DMC | \\172.24.11.10\Sterlite\Governance\Monthly Governance
23 | WSR | WK63_2020_02_17_WSR_RVM | On-Going | 2018-12-11 | 2020-02-17 | NA | Shyam Garg | DMC | \\172.24.11.10\Sterlite\Governance\WSR
24 | MoM of Workshop | Multiple files | Completed | 2018-12-03 | 2020-01-24 | NA | Deepak Browne | DMC | \\172.24.11.10\Sterlite\Minutes of Meeting
25 | Mediation SNMP Trap List | Mediation_SNMP trap List - RVM_v0.1 | Completed | 2018-12-18 | 2018-12-24 | NA | Ashish Kapadiya | DMC | \\172.24.11.10\Sterlite\Monitoring Tool
26 | Project Plan | 2020_01_02_RVM_Project_Plan_1.8 | On-Going | 2018-12-11 | 2020-01-02 | NA | Shyam Garg | DMC | \\172.24.11.10\Sterlite\Project Plan
27 | Mediation Product Manual | Product_Manual_v7.2.0 | Completed | 2018-12-24 | 2018-12-24 | NA | Ashish Kapadiya | DMC | \\172.24.11.10\Sterlite\Sterlite Mediation User Manual
28 | Test Strategy Document | RVM_Test_Strategy_v0.5.doc | Completed | 2019-04-11 | 2019-12-26 | NA | Ashish Kapadiya | DMC | \\172.24.11.10\Sterlite\Testing\Test_Strategy
29 | Architecture Deployment Document | STL_DMC_Architecture_Document_v1.1_30082019 | Completed | 2019-04-26 | 2019-08-30 | Sterlite to revert with ETL deployment architecture document | Sanket Bhavsar | DMC | \\172.24.11.10\Sterlite\Architecture Deployment Document
30 | Software Package Module Details | OS_Software_Package_Module_Details | Completed | 2019-06-03 | 2019-06-03 |  | Sanket Bhavsar | DMC | \\172.24.11.10\Sterlite\3_Infrastructure\9_OS_Software_Package_Module_Details | Pending for Confirmation from DMC side
31 | Mediation implementation & planning. | SterliteDependency-MediationImpl_03062019 | Completed | 2019-06-03 | 2019-06-03 | DMC to provide necessary details in document | Sanket Bhavsar | DMC | \\172.24.11.10\Sterlite\Mediation implementation & planning
32 | Operator Source/Data open points | OpenPoints_SourceWise_05072019 | Completed | 2019-06-11 | 2019-07-09 | DMC to provide necessary information | Sanket Bhavsar | DMC | \\172.24.11.10\Sterlite\SterliteDependency_OpenPoint
33 | Talend Presentation | talendppt.ppt | Completed | 2019-06-17 | 2019-06-17 | DMC will review and update | Deepak Browne | DMC | \\172.24.11.10\Sterlite\Talend
34 | Solution Design - HLD | HLD vs 4.0 | Completed | 2019-07-04 | 2019-08-30 |  | Deepak Browne | DMC | \\172.24.11.10\Sterlite\Solution Design\HLD
35 | SAP BI Deployment Document | SAP_BI_Deployment_Dcoument | Completed | 2019-07-08 | 2019-07-08 | DMC to confirm the document | Sanket Bhavsar | Pending | \\172.24.11.10\Sterlite\Architecture Deployment Document\Deployment Document
36 | Oracle RAC Deployment Document | RAC_Deployment_Document | Completed | 2019-07-08 | 2019-07-08 |  | Sanket Bhavsar | Pending | \\172.24.11.10\Sterlite\Architecture Deployment Document\Deployment Document
37 | Backup Software Training Agenda and Document | CommVault Backup Training Agenda DMC_CommVault_Backup_Software_Training_v1.0 DMC Cambodia-HDPS | Completed | 2019-07-15 | 2019-07-15 |  | Ajay Patel | Pending | \\172.24.11.10\Sterlite\3_Infrastructure\12_Backup Software Training Agenda and document
38 | Product Roadmap | ProdRoadmap3 Years | Completed | 2019-07-11 | 2019-07-11 |  | Shyam Garg | DMC | \\172.24.11.10\Sterlite\Product Roadmap
39 | Product Portfolio Statement | - STl_Product_Portfolio_Statement_of_Direction_12_DMC - STL-DAWN-Roadmap-19-20v2.0 | Completed | 2019-07-12 | 2019-08-06 |  | Shyam Garg | DMC | \\172.24.11.10\Sterlite\Product Roadmap
40 | Solution Design - LLD | LLD_V1.2 | In Progress | 2019-08-06 | 2019-10-21 |  | Deepak Browne / Ranga | In Progress | \\172.24.11.10\Sterlite\Solution Design\LLD
41 | Solution Design - Operator wise Configuration Specs | Multiple files | In Progress | 2019-08-06 | 2019-08-06 |  | Deepak Browne / Ranga | Pending | \\172.24.11.10\Sterlite\Solution Design\LLD\Operator wise Configuration Specs
42 | STL Solution Mediation Training Agenda | STL_Solution_Training_Agenda_RVM | Completed | 2019-11-13 | 2019-11-13 |  | Shyam Garg | Pending | \\172.24.11.10\Sterlite\Training\STL Solution Training Agenda
43 | Training on Configuration and Maintenance on HPE Server, Tape Library, Switches and Hitachi VSP-G600 Storage | Multiple files | Completed | 2019-09-19 | 2019-09-19 |  | EZY | DMC | \\172.24.11.10\Sterlite\Training\Hardware
44 | SAP BI Procurement Document for License | Amend to EUMA-25Oct2019 EUMA PE EULA Acceptance Form for Sell On Prem enAPJ.v.3-2019 (1) | Completed | 2019-10-25 | 2019-10-25 |  | Shyam Garg | Rajneesh | \\172.24.11.10\Sterlite\SAP BI Procurement
45 | Infra Training Completion Certificate | Infra_Training_Completion_Certificate_19Sep2019 | Completed | 2019-09-19 | 2019-09-19 |  | Shyam Garg | Rajneesh & Sophal | \\172.24.11.10\Sterlite\Training\Hardware\Infra Completion Certificate
46 | UAT Functional TCs Document | UAT_Functional_TC_V01 | In Progress | 2020-01-22 | 2020-01-31 | DMC to review | Mayura Dagade |  | \\172.24.11.10\Sterlite\UAT\Test Cases
47 | UAT Operator TCs Document | UAT_Operator_Smart_V02 | In Progress | 2020-01-22 | 2020-01-31 | DMC to review | Mayura Dagade |  | \\172.24.11.10\Sterlite\UAT\Test Cases
48 | Source wise Development Tracker | Source_Wise_Classification_17th Feb'20 | In Progress | 2020-02-07 | 2020-02-17 | STL to provide development status for all sources, SMART status shared as of now | Deepak Browne |  | \\172.24.11.10\Sterlite\Source wise Development Tracker
49 | ETL & DWH Test Cases Document | Etl+DWH-Testing-TestCases.xlsx | In Progress | 2020-02-12 | 2020-02-12 | ETL team tp provide for all stream, Recharge stream shared as of now | Ranga |  | \\172.24.11.10\Solution Design\Source data mapping\UAT\ETL DWH TEST CASE
50 | Source to Target mapping for recharge | FINAL_MAPPING_DOC_RECHARGE.xlsx | Completed | 2020-02-12 | 2020-02-12 |  | Vani |  | \\172.24.11.10\Solution Design\Source data mapping
51 | STL Solution ETL & DWH Training Agenda | TRAINING_AGENDA | Completed | 2020-02-14 | 2020-02-14 |  | Shyam Garg | Pending | \\172.24.11.10\Sterlite\Training\ETL

## Training
Sr.No | Training | STL submitted document name (Latest version) | Status | From Date | To Date | Trainer | Path | Attendes
1 | Backup Software Training | - DMC_CommVault_Backup_Software_Training_v1.0 - CommVault Backup Training Agenda | Completed | 2019-08-07 | 2019-08-08 | Ajay Patel | \\172.24.11.10\Sterlite\Training\Backup Software
2 | Infrastructure Hardware (HPE Server, Tape, Switches and Hitachi Storage) | Multiple Files | In Progress | 2019-09-18 | 2019-09-19 | ThetPaing Htut | \\172.24.11.10\Sterlite\Training\Hardware
3 | Commvault Backup Software Training |  |  | 2019-09-19 | 2019-09-19 | Mathew Varghese
4 | Mediation | Multiple Files | Completed | 2019-11-18 | 2019-11-19 | Sanket Bhavsar | \\172.24.11.10\Sterlite\Training\Mediation